## Summary
| Total |  |  |  | Coding |  |  |  | Meetings |  |  |  | Systems Analysis |  |  |  | Overhead
| Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit |  | Budgeted | Actual | Deficit
Bidhan | 8400 | 5650 | 2750 | Bidhan | 3200 | 2100 | 1100 | Bidhan | 1500 | 950 | 550 | Bidhan | 700 | 1300 | -600 | Bidhan | 3000 | 1300 | 1700
Todd | 12700 | 14400 | -1700 | Todd | 6200 | 6300 | -100 | Todd | 1500 | 1400 | 100 | Todd | 2000 | 3000 | -1000 | Todd | 3000 | 3700 | -700
Alex | 11900 | 12150 | -250 | Alex | 5900 | 5600 | 300 | Alex | 1500 | 1350 | 150 | Alex | 1500 | 2100 | -600 | Alex | 3000 | 3100 | -100
Mark | 11600 | 9200 | 2400 | Mark | 6000 | 4900 | 1100 | Mark | 1500 | 900 | 600 | Mark | 1100 | 1400 | -300 | Mark | 3000 | 2000 | 1000
Shan | 12500 | 12550 | -50 | Shan | 6200 | 5700 | 500 | Shan | 1500 | 1450 | 50 | Shan | 1800 | 2900 | -1100 | Shan | 3000 | 2500 | 500
Liz | 8600 | 7950 | 650 | Liz | 3200 | 2700 | 500 | Liz | 1500 | 1450 | 50 | Liz | 900 | 2300 | -1400 | Liz | 3000 | 1500 | 1500
Hengyi | 11900 | 12750 | -850 | Hengyi | 5600 | 5700 | -100 | Hengyi | 1500 | 1350 | 150 | Hengyi | 1800 | 2700 | -900 | Hengyi | 3000 | 3000 | 0
Total | 77600 | 74650 | 2950 | Total | 36300 | 33000 | 3300 | Total | 10500 | 8850 | 1650 | Total | 9800 | 15700 | -5900 | Total | 21000 | 17100 | 3900

## Gantt
Gantt Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Bidhan | 1 | Define Save System Requirements | Done | 2 | 2 | bar: 1 to 2
| 2 | Design Data Flow Diagrams | Done | 3 | 2 | bar: 3 to 4
| 3 | Implement Save Logic | Done | 4 | 6 | bar: 5 to 10
| 4 | Implement Load Logic | Done | 4 | 6 | bar: 11 to 16
| 5 | Load Game Button And Save Functionality | In Progress | 6 | 5 | bar: 17 to 21
| 6 | Create Data Storage Schema | Planned | 3
| 7 | Testing Save Functionality | Planned | 3
| 8 | Testing Load Functionality | Planned | 2
| 9 | Integration and System Testing | Planned | 2
| 10 | Deployment | Planned | 1
| 11 | User Documentation and Training | Planned | 2
| 12 | Total |  | 32 | 21
Todd | 13 | Requirements | Done | 3 | 3 | bar: 1 to 3
| 14 | Program NPC Manager | Done | 5 | 6 | 4: 13
| 15 | Program Game Object Manager | Done | 2 | 4 | 4: 13
| 16 | Program NPCs superclass | Done | 2 | 4 | 4: 13
| 17 | Program NPC dialogue system | Done | 10 | 14 | 10: 14
| 18 | Programming NPC combat response | Done | 10 | 6 | 10: 14
| 19 | Programming NPC dialogue for The Wolf | Done | 2 | 3 | 24: 17
| 20 | Programming NPC dialogue for The Bear | Done | 2 | 1 | 27: 19
| 21 | Programming NPC dialogue for The Hiker | Done | 2 | 2 | 28: 20
| 22 | Programming NPC dialogue for The Hunter | Done | 2 | 2 | 28: 20
| 23 | Programming NPC dialogue for The Wizard | Done | 2 | 2 | 28: 20
| 24 | Programming NPC dialogue for The Hippie | Done | 2 | 2 | 28: 20
| 25 | Programming NPC dialogue for The Axman | Done | 2 | 2 | 28: 20
| 26 | Programming NPC dialogue for The Cat | Done | 2 | 2 | 28: 20
| 27 | Programming NPC dialogue for The Owl | Done | 2 | 2 | 28: 20
| 28 | Programming NPC dialogue for The Fish | Done | 2 | 2 | 28: 20
| 29 | Testing | Done | 10 | 6 | 10: 14
| 30 | Total |  | 62 | 63
Alex | 31 | Determine requirements and constraints for levels and movement | Done | 3 | 2 | bar: 1 to 2
| 32 | Program levelLoader and terrainObjects Classes | Done | 5 | 10 | 3: 31
| 33 | Programming environmental objects that are stagnant but may cause damage or impede player movement | Done | 1 | 1 | 13: 32
| 34 | Programming a movable player object that interacts with environmental objects | Done | 8 | 2 | 14: 32
| 35 | Programming moving platforms between terrain areas on the same level | Done | 2 | 5 | 16: 32
| 36 | Programming death event for falling off the map or impacting deadly environmental objects | Done | 2 | 3 | 21: 32
| 37 | Programming passageways for additional levels or map areas | Done | 5 | 4 | 24: 32
| 38 | Programming locked passageways hiding and preventing movement through passageways | Done | 3 | 2 | 28: 32
| 39 | Programming and initializing Level 1 | Done | 4 | 6 | 30: 33, 34, 35, 36, 37, 38
| 40 | Programming and initializing Level 2 | Done | 4 | 5 | 36: 33, 34, 35, 36, 37, 38
| 41 | Programming and initializing Level 3 | Done | 4 | 3 | 41: 33, 34, 35, 36, 37
| 42 | Programming and initializing Level 4 | Done | 4 | 3 | 41: 33, 34, 35, 36, 37
| 43 | Programming and initializing Level 5 | Done | 4 | 2 | 41: 33, 34, 35, 36, 37
| 44 | Testing | Done | 10 | 8 | 44: 39
| 45 | Total |  | 59 | 56
Mark | 46 | Basic Character Customization | Done | 6 | 10 | bar: 1 to 10
| 47 | Create Prefabs for Each Character | Done | 6 | 5 | 11: 46
| 48 | Implement Character Into Gameplay | Done | 16 | 12 | 16: 46,47
| 49 | Implement Combat with NPCs | Done | 6 | 2 | 28: 46,47,48
| 50 | Create Health Bar | Done | 2 | 3 | bar: 30 to 32
| 51 | Implement Health Bar into Gameplay | Done | 6 | 3 | 33: 50
| 52 | Expand Character Customization (Track Combat Stat, etc.) | Done | 4 | 3 | 33: 51
| 53 | Finalize Special Cases (Respawning when Health == 0, etc.) | Done | 6 | 4 | 33: 46
| 54 | Finalize Tracking Stats | Done | 6 | 3 | 33: 51,52
| 55 | Testing | Done | 2 | 4 | bar: 33 to 36
| 56 | Total |  | 60 | 49
Shan | 57 | Requirements Collection | Done | 3 | 4 | bar: 1 to 4
| 58 | Make sprites for items | Done | 7 | 8 | bar: 5 to 12
| 59 | Program effects for Power-Ups + PoisonApple | Done | 3 | 3 | bar: 5 to 7
| 60 | Program all Item reactions to Player collision – item description text placeholder, Use Now vs. Store for Later | Done | 2 | 2 | bar: 5 to 6
| 61 | Program Initial Inventory System and subclasses | Done | 8 | 3 | bar: 5 to 7
| 62 | Program result of Player clicking Use Now and Player clicking Store Later on all other powerups | Done | 3 | 2 | 8: 60,61
| 63 | Program how/when Inventory is displayed | Done | 1 | 1 | 10: 61,62
| 64 | Program functionality of adding items to Inventory with sprites | Done | 4 | 4 | 11: 58,62,63
| 65 | Program effect of Player trying to add too many items to Inventory excluding Collectibles | Done | 1 | 2 | 15: 64
| 66 | Program removal of item from inventory | Done | 2 | 1 | 15: 61,63,64
| 67 | Program placeholder for text shown when item is selected in Inventory | Done | 2 | 3 | 15: 63,64
| 68 | Program automatic addition to Inventory for Collectibles with message (even if Inventory is full) | Done | 2 | 1 | 16: 64,65
| 69 | Program increase in Inventory slots when clueCount increases | Done | 4 | 3 | 11: 63,65
| 70 | Program result of Player clicking Use Now on Golden Apple (depends on health) and Player Clicking Store Later | Done | 2 | 5 | 7: 60
| 71 | Program result of Player clicking Use on Golden Apple in Inventory (depends on health) | In Progress | 1 | 2 | 15: 61,63,64
| 72 | Program Collectibles check for The Cat ending | Done | 4 | 2 | 17: 68
| 73 | Add pop-up messages for SecretScroll and StoryBook | Done | 3 | 5 | bar: 5 to 9
| 74 | Testing | Done | 10 | 6 | bar: 19 to 24
| 75 | Total |  | 62 | 57
Liz | 76 | Requirements | Done | 5 | 3 | bar: 1 to 3
| 77 | Creating Visual Main Menu Screen | Done | 3 | 5 | bar: 4 to 8
| 78 | Coding Main Menu behavior scripts | Done | 2 | 4 | 9: 77
| 79 | Creating Pause menu Screen | Done | 2 | 5 | bar: 13 to 17
| 80 | Coding Pause menu behavior and scripts | Done | 3 | 2 | 18: 79
| 81 | Creating inventory button and menu | Done | 2 | 1 | 20: 79; 21: 80
| 82 | Coding Inventory button and behavior script | In progress | 3
| 83 | Designing Victory Screen | Done | 1 | 1 | bar: 20
| 84 | Coding Victory Screen behavior scripts | Done | 3 | 1 | bar: 21
| 85 | Designing Game Over Screen | Done | 1 | 1 | bar: 21
| 86 | Coding Game Over screen behavior scripts | Done | 3 | 1 | 22: 87
| 87 | Testing | Done | 4 | 3 | 23: 79; 24: 80
| 88 | Total |  | 32 | 27
Hengyi | 89 | Requirements Collection | Done | 5 | 5 | bar: 1 to 5
| 90 | Environment elements design and audio collection | Done | 5 | 5 | 6: 89
| 91 | Environment Manager Design | Done | 6 | 6 | 8: 89
| 92 | Audio Manager Design | Done | 5 | 5 | 11: 89
| 93 | Scene Engine Implementation | Done | 10 | 10 | 7: 89
| 94 | Weather Implementation | Done | 2 | 4 | 17: 93
| 95 | Battle Scene Implementation | Done | 2 | 3 | 20: 93
| 96 | Background Implementation | Done | 2 | 2 | 18: 93
| 97 | Background Music Implementation | Done | 2 | 2 | 18: 93
| 98 | Sound Effect Implementation | Done | 2 | 4 | 17: 93
| 99 | Testing and Optimization | Done | 5 | 4 | 21: 98
| 100 | Demo mode | Done | 5 | 4 | 22: 98
| 101 | Final Integration | Done | 5 | 3 | 22: 98
| 102 | Total |  | 56 | 57
103
104
105
106
107
108
109
110

## SA
Systems Analysis Chart
|  | Task | Status | Predicted (hrs) | Time Spent (hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70
Bidhan | 1 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 2 | Class Diagram | Done | 3 | 6 | bar: 3 to 8
| 3 | Champion | Done | 2 | 4 | bar: 9 to 12
| 4 | Sequence Diagram | Done | 1 | 1 | bar: 13
| 5 | Total |  | 7 | 13
Todd | 6 | Install Unity | Done | 1 | 1 | bar: 1
| 7 | Make Version 1.0 of RFP | Done | 1 | 1 | bar: 2
| 8 | Update RFP to Version 2.0 | Done | 1 | 1 | bar: 3
| 9 | Champion | Done | 8 | 15 | bar: 4 to 18
| 10 | Class Diagram | Done | 2 | 3 | bar: 19 to 21
| 11 | Diagram 0 | Done | 4 | 5 | bar: 22 to 26
| 12 | Class Diagram v2 | Done | 1 | 2 | bar: 27 to 28
| 13 | Sequence Diagram | Done | 2 | 2 | bar: 29 to 30
| 14 | Total |  | 20 | 30
Alex | 15 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 16 | Update RFP to Version 3.0 | Done | 1 | 2 | bar: 3 to 4
| 17 | Class Diagram | Done | 6 | 5 | bar: 5 to 9
| 18 | Champion | Done | 5 | 10 | bar: 10 to 19
| 19 | Sequence Diagram | Done | 2 | 2 | bar: 20 to 21
| 20 | Total |  | 15 | 21
Mark | 21 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 22 | Class Diagram v1 | Done | 3 | 1 | bar: 3
| 23 | Champion v1 | Done | 5 | 10 | bar: 4 to 13
| 24 | Sequence Diagram | Done | 2 | 1 | bar: 14
| 25 | Total |  | 11 | 14
Shan | 26 | Install Unity | Done | 2 | 2 | bar: 1 to 2
| 27 | Class Diagram v1 | Done | 3 | 3 | bar: 4 to 6
| 28 | Update RFP | Done | 2 | 1 | bar: 7
| 29 | Champion | Done | 7 | 13 | bar: 8 to 20
| 30 | Class Diagram v2 | Done | 1 | 4 | bar: 21 to 24
| 31 | Sequence Diagram | Done | 1 | 1 | bar: 25
| 32 | Create Schedule Charts | Done | 2 | 5 | bar: 3; 26 to 29
| 33 | Total |  | 18 | 29
Liz | 34 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 35 | Update RFP to Version 5.0 | Done | 2 | 1 | bar: 3
| 36 | Class Diagram | Done | 3 | 10 | bar: 4 to 13
| 37 | Champion | Done | 2 | 6 | bar: 14 to 19
| 38 | Sequence Diagram | Done | 1 | 4 | bar: 20 to 23
| 39 | Total |  | 9 | 23
Hengyi | 40 | Install Unity | Done | 1 | 2 | bar: 1 to 2
| 41 | Update RFP to Version 4.0 | Done | 2 | 3 | bar: 3 to 5
| 42 | Class Diagram v1 | Done | 1 | 2 | bar: 6 to 7
| 43 | Class Diagram v2 | Done | 2 | 2 | bar: 8 to 9
| 44 | Champion | Done | 10 | 16 | bar: 10 to 25
| 45 | Sequence Diagram | Done | 2 | 2 | bar: 26 to 27
| 46 | Total |  | 18 | 27
47
48
49
50
51
52
53
54
55

## Meetings
Team Meetings
| Date | 2025-02-05 | 2025-02-07 | 2025-02-12 | 2025-02-14 | 2025-02-17 | 2025-02-19 | 2025-02-26 | 2025-03-19 | 2025-03-26 | 2025-04-02 | 2025-04-09 | 2025-04-16
|  | Diagram 0 and Champion Discussion | Class Diagram Reviewing w/BC | SA Presentation Planning | Champion and Storyboard Reviewing w/BC | SA Pres Review w/BC | MVP Discussion | Plan out work for next week | Boundary Test Discussion | Coding Standards and General Prep | Dynamic Binding and Debugging | Tying up loose ends | Post Mortem discussion
| Hours | 2 | 2.5 | 1.5 | 1.5 | 0.5 | 1.5 | 1 | 1 | 1 | 1 | 0.5 | 1
Bidhan | 9.5 |  | 2 | TRUE |  |  | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE
Todd | 14 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
Alex | 13.5 | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE
Mark | 9 | TRUE |  | TRUE | 0.5 |  | TRUE | TRUE | TRUE | TRUE |  | TRUE | FALSE
Shan | 14.5 | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Liz | 14.5 | TRUE | 2 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
Hengyi | 13.5 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE |  | TRUE | TRUE | TRUE | TRUE | TRUE
Total | 88.5 | 12 | 14 | 10.5 | 8.5 | 1.5 | 10.5 | 5 | 7 | 6 | 5 | 3.5 | 6
89.5

## Overhead
Overhead
| Bidhan | Todd | Alex | Mark | Shan | Liz | Hengyi
Training | 8 | 8 | 8 | 8 | 8 | 8 | 8
SA Presentation Prep | 5 | 6 | 5 | 7 | 2 | 2 | 6
Team Lead Weekly Report Presentation Prep |  |  |  |  | 4 |  | 6
Team Lead Lecture Presentation Prep |  | 15 | 10 | 5 | 10 | 5 | 10
Github Troubleshooting |  | 8 | 8 |  | 1
Total | 13 | 37 | 31 | 20 | 25 | 15 | 30

## Deliverables
Deliverables
| TL1 Deliverables | TL2 Deliverables | TL3 Deliverables | TL4 Deliverables | TL5 Deliverables | TL6 Deliverables
| Date Due: | Date Due: 2/25 | Date Due: 3/20 | Date Due: 3/27 | Date Due: 4/3 | Date Due:
|  | Have a function that the MVP can call in GIT | Have 2 boundary tests and 1 stress test | Make sure code follows coding standards | Have example of dynamic binding in code
Deliverable Tracker
|  | Bidhan | Todd | Alex | Mark | Shan | Liz | Hengyi
TL 1
| TL 2 | ü | ü | ü | ü | ü | ü | ü
| TL 3 |  | ü | ü | ü | ü | ü | ü
| TL 4 |  | ü | ü | ü | ü | ü | ü
| TL 5 |  | ü | ü |  | ü |  | ü
TL 6